## Timeline
WorkPackages | Description | M 1 | M 2 | M 3 | M 4 | M 5 | M 6 | M 7 | M 8 | M 9 | M 10 | M 11 | M 12
WP-1: Research Ethics | IRB application | bar: M 1
WP-2: Development | Purchaching Equipment | bar: M 1 to M 2
Developing study protocol | bar: M 1 to M 2
WP-3: Conduction | Recruiting participants | bar: M 2 to M 11
Assessments | bar: M 2 to M 11
Experiment Conduction | bar: M 2 to M 11
WP-4: Data analysis | Signal Processing | bar: M 4 to M 12
Machine Learning | bar: M 4 to M 12
Statistic analysis | bar: M 4 to M 12
WP-5: Writing Reports | Manuscript | bar: M 11 to M 12
Conference Paper | bar: M 11 to M 12
Current Colloborators | This needs to be changed to reflect current invvolvement. Spell out organizations and include MIDB
?
ICI
ICD
ECE
Testing room | Testing room for protcol implementation: We will need at least 90 minutes of access to testing rooms for assessments with each participant . Overall, for testing and consent for 20 participants we will require 30 hours for testing.
Experiment (EEG room) | "The total duration of the BCI experiment for each participant (~100 min or 1:40 hour for each participant). EEG: 45-min (preparation and wearing cap) + 3(15-min recording sessions) + 2(5-min breaks). The budget is based on 20 participants to account for attrition
30

## One-year Budget
University of Minnesota
A Feasibility Study: Using Brain Computer Interface For Communication In Non-Speaking Autistic (NSA) Population
BUDGET DETAIL
|  | Full FTE | FTE | ARRT Fellowship | MIDB COST | TOTAL (inkind) COST | Salary | Total Cost
PERSONNEL
| Maryam, Mahmoudi.Ph.D, ARRT Postdoctoral Associate, Institute on Community Integration (ICI), [PI] | in-kind |  | 20% |  | 10454.6 | 52273
| Renata Ticha, Ph.D, Research Associate, Co-director of the Global Resource Center for Inclusive Education, Co-director of the Research and Training Center on Outcome Measures, Institute on Community Integration (ICI); [Project Mentor] | donated time (2hr/week) | 0% |  |  | 0
| Brian Abery, Ph.D., Research Manager 3, Co-director Research and Training Center on HCBS Outcome Measurement, Co-director, Global Resource Center for Inclusive Education; Director ARRT Fellowship Program[Projec Mentor] | donated time (2hr/week) | 0% |  |  | 0
| Vassilios, Morellas, Ph.D, Research Professor, Department of Electrical and Computer Engineering and Center Director of the Robots and Sensors for Human Well-Being (ROSE-HUB), [Co-PI] | in-kind | 4% |  |  | 7527.6 | 188190
| TBH 1-2 Undergraduate Research Assist. @ $15/hr. for 576 hours for 9 months. |  |  |  | 3225
| Subtotal |  |  |  | 3225 | 17982.2
Fringe
| 36.8%, Faculty and P & A - Abery |  |  |  | 0
| 36.8%, Faculty and P & A - Ticha |  |  |  | 0
| 36.8%, Faculty and P & A - Morellas |  |  |  |  | 2770.1568
| 25.7%, Postdoctoral Associate - Mahmoudi |  |  |  |  | 2686.8322
0% Undergrad Reseatch Asst.
| Subtotal |  |  |  |  | 5456.989
Consultants
| Ahmadreza Keihani, Ph.D, Tehran University of Medical Sciences | in-Kind
| Kevin Pitt, PhD, CCC-SLP, Assistant Professor, Director of the AAC Translation Lab, Special Education & Communication Disorders, University of Nebraska–Lincoln | in-Kind
| Jolene Hyppa Martin, Ph.D, CCC-SLP, Associate Professor Communication Sciences, Head of Augmentative and Alternative Communication (AAC) Clinic, University of Minnesota-Duluth | in-Kind
Subtotal
Cores & Services
| MIDB Analytics Core services, directed by Mark Fiecas, PhD, Assistant Professor, Division of Biostatistics |  |  |  | 6000
| MIDB Telehealth Core, directed by Jessica Simacek, Ph.D, [Co-PI] |  |  |  | 1507.5
| Participant inducements ($50/per each participant) |  |  |  | 1000
| EEG services (including using EEG, wearing and running EEG, extracting data), 20 persons, 44 hours, $70 per hour |  |  |  | 3080
| EEG technician assistant ($70 per hour), including fringe |  |  |  | 3080
| Subtotal |  |  |  | 14667.5
Equipment
| Hardware board, plus software, experiment kit |  |  |  | 300
| USB-6002 16-Bit 50 kS/s Multifunction I/O and NI-DAQmx |  |  |  | 515
| 4 Back light LED (2.5*2.5 cm)- Red color [C-E-Back-Light] |  |  |  | 25
| Standard 12 pictures |  |  |  | 200
| Subtotal |  |  |  | 1040
| MIDB FUNDING REQUEST |  |  |  | 19972.5
| ARRT FELLOWSHIP FUNDING |  |  | 13141.4322
| Inkind contributions |  |  |  |  | 10297.7568
| TOTAL COSTS | [6 empty] | 43411.689
43411.689

## Budget Justification
Personels
Renata Ticha | Renata Tichá, Ph.D., Co-Principal Investigator is a Research Associate at ICI with extensive experience in services to persons with disabilities as a program evaluator and researcher. She holds a doctorate in Special Education and has worked at the ICI for 13-years, coordinating and directing projects involving survey, assessment, and intervention research. Dr. Tichá has (co)authored publications on outcome assessment as well as directing research undertaken by the ICI’s RTC on Community Living. Dr. Ticha’s work on the National Core Indicators data set has led to significant enhancement in the manner in which we measure the outcomes of adults with IDD and our knowledge of the impact of Federal, State, and local policies on person’s lives. Her recent work includes study of NCI data set, the development of improved personal and systems-level HCBS outcome measures, and the evaluation of a variety of interventions designed to enhance the stability of the direct service workforce who support adults with IDD. In addition to contributing to product development, Dr. Tichá will mentor all evaluation activities including data collection and assessment, and assume responsibility for overseeing data management. She will also work with Dr. Abery in overseeing budgetary and contract matters.
Maryam Mahmoudi | Maryam Mahmoudi, Ph.D., PI and Project Coordinator. Maryam Mahmoudi has a Ph.D. in psychology and is an ARRT postdoctoral associate at the ICI. Prior to this she was a postdoctoral fellow at the Social Robotics Lab at the NTNU, Norway. Dr. Mahmoudi currently works on a variety of projects including evaluation of the use of smart living technologies for people with disabilities and the use of robotics to support people with disabilities in ther employment. She has a decade of experience in interdisciplinary research. For her master degree, she developed an online expert system for screening autism for her country of origin, Iran. Subsequently she initiated a collaboration with the Advanced Robotics and Intelligent Systems Program on projects focused on using a robot to screen autism in children and teach basic social skills to those with this disability. During her fellowship, she gained experience of working with a Nao robot to teach advanced social problem solving skills to children with autism and provide cognitive stimulation interventions for ageing adults. For the current project, she will assume responsibility for recruiting participants, coordinating project activities, developing program and study protocol in a teamwork on a day to day basis.
Vassilis Morellas | Vassilis Morellas, Ph.D. - CS & E. Dr. Vassilios Morellas is a Research Professor in the Department of Electrical and Computer Engineering and Center Director of the Robots and Sensors for Human Well-Being (ROSE-HUB). His research interests are in the area of geometric image processing, machine learning, robotics and sensor integration to enhance automation of electromechanical systems. His past research experience also includes work on Intelligent Transformation Systems where he developed innovative technologies to reduce run off the road accidents. Dr. Morellas obtained his B.S. in Mechanical Engineering from the National Technical University of Athens, Greece, his MSME from Columbia University, NY and his PhD from the Department of Mechanical Engineering at the University of Minnesota. He publishes regularly in peer review conference proceedings and journals and has coauthored a book on camera programming. Dr. Morellas will provide expertise on Machine Learning techniques for analyzing the components of brain signal patterns. Also, he guides his students for BCI setup and assisting during experiments.
Brian Abery | Brian Abery, Ph.D., Principal Investigator, Project Director. Brian Abery is the Director of the Research and Training Center on HCBS Outcome Measurement (RTC/OM), and Co-Director of the National Center on College Students with Disabilities (NCCSD) and the Global Disabiity Rights and Inclusion Program (GDRIP) at the Institute on Community Integration (ICI). He has been Principal Investigator of numerous projects designed to enhance the self-determination, educational inclusion, transition, and employment of youth and adults with disabilities, better understand the impact of care coordination on the health outcomes of members of this population, and how to support them in the achievement of post-secondary goals and adult life. His most recent related projects have focused on how to effectively use robotics to support people with disabilities in customized and supported employment in collaboration colleagues from the University ot Tokyo and OryLabs in Japan, and understanding the impact of Smart Living Technology on the self-determination, social inclusion, and independence of adults with IDD. Dr. Abery holds a doctorate in educational psychology and has an extensive background in research, program development, and evaluation. He is currently or in the recent past has been the PI or Co-PI on NIDILRR (smart home technology, HCBS Outcome Measurement; Self-determination); U.S. Department of State (Self-Determination, Response to Intervention and Inclusive Education), Administration on Community Living (Transition, NCCSD), UNICEF, and UKAID projects. In addition to contributing heavily to the content development, Dr. Abery will mentor the overall project, evaluation/assessment activities taking place as part of the project data collection, and data analysis. In addition, he will work together with Dr. Ticha to mentor day-to-day efforts of project staff as well as serve as the liaison between collaborating University departments and community organizations.
TBD Undergraduae Research Assis | Student will help set up BCI, run BCI, connecting devices, trouble shooting, assist the experiments , every student could help with around 30 hours monthly and overall, 272 hours for 9 months. |  | 1500
Consultant
Ahmadreza Keihani | Ahmadreza Keihani is a candidate at Tehran University of Medical Sciences (TUMS), Biomedical Engineering. His research interest fields are nonlinear dynamics and chaos, EEG and biological data science, Brain Computer Interface (BCI) and Neuroimaging. His Ph.D. thesis was focused on finding the nonlinear coupling between brain and muscles activities in ALS patients using nonlinear dynamics and chaos analysis (Joint EE-EMG, MRI study). During the current project, he will provide consultation on BCI task design and protocol.
Kevin Pitt | Kevin Pitt, Ph.D., CCC-SLP is the director of the Augmentative and Alternative Communication Translation (AACT) Lab atht e University of Nebraska-Lincoln. His research focuses on the development and implementation of AAC devices for adults and children with severe physical impairments. Kevin's long-term goal for the AACT Lab is to translate new AAC access technologies, with a primary focus on brain-computer interface (BCI) technologies, out of the laboratory setting and into clinical practice. These efforts hope to support the smooth incorporation of BCI into existing clinical practices alongside existing AAC techniques, and support fully inclusive access options across the lifespan. In addition to his research, Kevin teaches Anatomy & Physiology of Speech & Hearing, while co-teaching the Augmentative & Alternative Communication (AAC) course. Prior to arriving at Nebraska, Kevin spent five years as a graduate research assistant at the Speech and Applied Neuroscience Lab at the University of Kansas. He began his career as a Radiologic Technologist and a Magnetic Resonance Imaging (MRI) Technologist at St. Louis University Hospital, before transitioning to a career in speech-language pathology. For the current project, he will support the project with consultation regarding BCI-AAC design, methodology, EEG adaptation for adolescents with disabilities and guidlines for a standard BCI-AAC study.
Jolene Hyppa Martin | Jolene Hyppa Martin, Ph.D., CCC-SLP, Associate Professor Communication Sciences, Head of Augmentative and Alternative Communication (AAC) Clinic, University of Minnesota-Duluth. She has over a decade of experience as a licensed speech-language pathologist who focuses on augmentative and alternative communication for individuals with severe communication disabilities, has earned a PhD in this area, hold a certificate of clinical competence from the American Speech-Language-Hearing Association, and serve in a leadership role in the Minnesota Speech-Language-Hearing Association’s Augmentative and Alternative Communication Committee. She will provide support regarding communication assessment, picture selections, task design and AAC and related areas.
Services & Cores
Participant inducements ($50/per each participant) | To compensate partially participants' time and their transportation expenses.
EEG services | The total duration of the experiment for each participant (~130 min or 2:10 hour for each participant): Because of sensitivities of the participant, each person exposes half hour to EEG cap to see if they are comfortable with it. EEG: 30-min(familarity)+45-min (preparation and wearing cap) + 3(15-min recording sessions) + 2(5-min break). We write the budget for 20 participants if we consider to lose some participants or data. Overall for 20 persons, we need 44 hours access for EEG. | These hours are not consistent with what you have listed in the budget. Please correct
EEG technician assistant | An EEG technician from MIDB will be assigned to help with setup of EEG, data recording for 20 participants. Overall, the assistant will help for 44 hours of conducting experiments. | Who is this EEG assistant and how will the individual be paid
Jessica Simacek | Jessica Simacek serves as the Director of the ICI-led TeleOutreach Center and the TeleOutreach Research Core at the Masonic Institute for the Developing Brain. Dr. Simacek is the Principal Investigator on research projects related to the use of innovative distance-learning technologies to improve access to interventions for children with developmental disabilities or complex communication needs and for their families. She serves as a faculty mentor to fellows in the MN Leadership Education in Neurodevelopmental Disabilities (MN-LEND) program and her work has appeared widely in peer-reviewed journals focusing on intervention research. She has a Ph.D. in Educational Psychology, Special Education, from the University of Minnesota, and is a former MN-LEND fellow. She will support the experiment design, protocol development and on-going consultation on AAC methodology for participants in this project.
Mark Fiecas | Mark Fiecas, PhD, is the Co-director of the MIDB Analytics Core. The focus of his research is to understand the structure and function of the human brain through the use of imaging technology. His experience with neuroimaging research spans a broad range of areas, from studying the connectivity of the human brain to investigating genetic underpinnings of brain phenotypes. His interdisciplinary research focuses on functional connectivity and imaging genetics. From a methodological perspective, his primary interest is in time series analysis. For the current project, he will support analyzing data from EEG, including preprocessing and signal analysis
Equipment & Supplies
Hardware board, plus software, experiment kit | Task design set up; Hardware board for playing the visual stimulus on LEDs (Driver borad)
USB-6002 16-Bit 50 kS/s Multifunction I/O and NI-DAQmx | NIDAQ (16 Bit) for anlaog to digital and digital to analog converting and recording rhe triger pulses. This provides combinations of analog I/O, digital I/O, and counter/timer functionality in a single device for computer-based systems. The Multifunction I/O Device features I/O with varying channels, sample rates, output rates, and other features to meet many common measurement requirements. You can use the device for industry applications such as laboratory automation, research, and design verification. The included DAQExpress companion software provides basic measurement and analysis, while the included NI-DAQmx driver provides the ability to create customized automated measurement and control applications. NI-DAQmx supports NI programming environments as well as Python, ANSI C, C#.NET, and MathWorks MATLAB® software.
4 Back light LED (2.5*2.5 cm)- Red color [C-E-Back-Light] | These lights (4 red LED lights) will be set on the monitor as shown in the project plan.
Standard 12 pictures | These pictures will be used for our project to display on the monitor.

## resources shared by colleagues
Jessica | https://cehs.unl.edu/aactranslation/ | Use last names e.g. Dr. XXXXXX
Kevin | In the lab currently my work primarily focuses on P300-based BCI-AAC to pictorial and spelling-based systems to support those both with and without literacy skills. During my dissertation the work with my mentor was more motor(imagery)/mu based, to provide switch type access to AAC. One of my big interests though is to understand what makes individuals best suited to different BCI-AAC techniques, along with avenues for BCI-AAC translation. Such at these types of work – https://digitalcommons.unl.edu/specedfacpub/193/ https://digitalcommons.unl.edu/specedfacpub/233/
The Unciron speller from gtec is one of the only commercially available BCI systems (I have not used it personally). It has some programming options, but I think its pretty limited. I am not sure if the Cognixion 1 is available yet, though that looks like another literacy-based system. So, you may have to develop a custom BCI solution depending on your intent. https://www.unicorn-bi.com/speller/ https://one.cognixion.com/ For a P300 systems, you could choose how many images you want, though fewer items may reduce novelty and the P300 effect to a degree. They are currently working on BCI access to Prentke Romich brand AAC devices (as I mention in the Implementation science paper), but as far as I know that’s all still in the development stage. https://onlinelibrary.wiley.com/doi/pdf/10.1002/pmrj.12525?casa_token=bM5zxai6YakAAAAA:c0JBHVOLABPr_Uz1jSkNefJoihzx3U3UywOE2sE4cEy3X3Sca7zxztLD9fXwPOG_DUvsDY8f2Jga2yA
That’s the P300 speller software we use in the lab. It is pretty flexible, but not sure about pictorial stimuli. Still there is a helpful wiki/forum you may be interested in looking into. https://www.bci2000.org/mediawiki/index.php/Main_Page https://www.bci2000.org/bbs/
https://pixabay.com/
Jolene | For assessing expressive and receptive communication I often use instruments like the Peabody Picture Vocabulary Test and the Receptive One Word Picture Vocabulary Test. Depending on age, I may use the Preschool Language Scale, The MacArthur-Bates Communicative Development Inventories, The Test of Aided Communication Symbol Performance, and the Interaction Checklist for AAC. I also use numerous, customized informal tasks to assess receptive joint attention; simple discrimination of objects, pictures, words; turn-taking; following functional spoken instructions; functional use; representational play; combinatorial play; Identical and non-identical match-to-sample tasks; and comprehension of who, what, where questions; vocal imitations; motor imitation; symbol type and size assessments (sometimes with the AAC Genie App), and so on. The committee that I co-chair created and maintains a repository of free, evidence-based AAC resources (including some assessment resources) that you might find helpful: https://sites.google.com/view/mnaacr/home I also attached a picture of the text I referred to when we met. It has information about assessments, match-to-sample tasks, and other information that may be useful.
There are many free developmental checklist assessments that are free- you could go to the repository I sent in the previous email and click on assessment to check them out. However, typically all norm referenced standardized tests are going to be quite expensive. Is there any chance that Jessica or folks in ICI have access to tests? Or perhaps you could ask a librarian. Sometimes the library has access to resources. Another idea might be to see if the SLHS Department may have student interns who need assessment hours who could do the testing with their test materials.